## ITEC1003Timeline
ITEC 1003
|  | Start Date | 2021-08-30
|  | End Date | 2021-12-29
| Fill in the Start Date and End Date |  |  | Task working on | Extra | Projected | Actual
|  |  | Planned Date | at start of day | Hours | Hours | Hours
Module 1: Computer Basics and Project Management |  | 21 hrs
#1 | Welcome | 0.25 | 2021-08-30 | 2021-08-30 | 0 | 0.25 | 0.25
| Orientation | 1 | ` | ` | 0.75 | 1.25 | 0.5
| Tour | 0.5 | ` | ` | 1 | 1.75 | 0.75
| Getting signed on, Office 365 activation | 0.75 | ` | ` | 1.5 | 2.5 | 1
| Look at Canvas, structure, location of the book | 0.5 | ` | ` | 1.75 | 3 | 1.25
#2 | Project and time management, milestones, timelines | 0.5 | ` | ` | 2 | 3.5 | 1.5
| Timeline activity, start tracking time | 1 | ` | ` | 2.75 | 4.5 | 1.75
| M1 PM reading and Beyond the Book | 0.5 | ` | ` | 3 | 5 | 2
| Ch 1: history | 0.5 | ` | ` | 3.25 | 5.5 | 2.25
| Read Ch 1 | 0.5 | ` | ` | 3.5 | 6 | 2.5
#3 | Ch 1 BTB: cloud computing | 1 | 2021-09-01 | 2021-09-01 08:03 | 4 | 7 | 3
| Ch 1 BTB: UT data privacy law | 1 | ` | ` | 4.5 | 8 | 3.5
| Read Ch 2 | 1 | ` | ` | 5 | 9 | 4
#4 | Ch 2 LAB: Handling Components / ESD | 1 | 2021-09-03 | ` | 5 | 10 | 5
| Ch 2 BTB: workplace safety | 1 | ` | ` | 5.75 | 11 | 5.25
| Read Ch 3 | 1 | ` | ` | 6.25 | 12 | 5.75
#5 | Ch 3: Lab to take apart a PC | 3 | 2021-09-08 | 2021-09-03 | 8 | 15 | 7
#6 | Read Ch 4 | 1 | 2021-09-10 | 2021-09-01 | 8.5 | 16 | 7.5
| Ch 4 BTB: File Naming Conventions | 1 | ` | ` | 9 | 17 | 8
| Review for Module 1 exam | 1 | ` | ` | 9 | 18 | 9
#7 | Review for Module 1 exam | 1 | 2021-09-14 | 2021-09-03 | 10.5 | 19 | 8.5
| Module 1 Exam (need 61 to pass) | 1 | ` | 2021-09-14 | 10 | 20 | 10
| Learn how to complete Module Completion Form | 0.5 | ` | ` | 10.25 | 20.5 | 10.25
| review of results, signing off module | 0.5 | ` | ` | 10.5 | 21 | 10.5
|  | Module End Date | 2021-09-14 | 2021-09-14 | 10.5 | 21 | 10.5
Module 2: Setting Up and Using Computers |  | 21 hrs
#8 | Ch 5 reading | 1.5 | 2021-09-16 | 2021-09-08 | 1 | 1.5 | 0.5
| Ch 5 BTB: Accessibility Options | 1.5 | ` | ` | 1.5 | 3 | 1.5
#9 | Ch 6 reading | 1.5 | 2021-09-20 | ` | 2 | 4.5 | 2.5
| Ch 6 BTB: Workplace Safety -- Ergonomics | 1.5 | ` | ` | 3 | 6 | 3
#10 | Ch 6 LAB: Thermodynamics, Conservation of Energy | 2 | 2021-09-22 | ` | 4.5 | 8 | 3.5
| CH 6 LAB: Patches and Updates | 1 | ` | ` | 5 | 9 | 4
#11 | Ch 7 reading | 1.5 | 2021-09-24 | ` | 6 | 10.5 | 4.5
| Ch 7 LAB: Mobile Devices | 1.5 | ` | ` | 7.25 | 12 | 4.75
#12 | Ch 8 reading | 2 | 2021-09-28 | 2021-09-14 | 8.75 | 14 | 5.25
| Ch 8 BTB: Permissions | 1 | ` | ` | 9.5 | 15 | 5.5
#13 | Ch 9 reading | 2 | 2021-09-30 | ` | 11.75 | 17 | 5.25
| Ch 9 BTB: Installing and Removing Software | 1 | ` | ` | 12.5 | 18 | 5.5
#14 | Review for Module 2 exam | 1 | 2021-10-04 | ` | 13 | 19 | 6
| M2 exam -- 92 questions in 1.5 hours (need 73.6 to pass) | 1.5 | ` | ` | 13.5 | 20.5 | 7
| review of results, signing off module | 0.5 | ` | ` | 13.75 | 21 | 7.25
|  | Module End Date | 2021-10-04 | 2021-09-14 | 24.25 | 42 | 17.75
Module 3: Networking, Security and Maintenance |  | 21 hrs
#15 | Ch 10 reading | 2 | 2021-10-06 | 2021-09-16 | 1.5 | 2 | 0.5
| Ch 10 BTB: How Internet and Web Work | 1 | ` | ` | 1.5 | 3 | 1.5
#16 | Ch 10 LAB: configure DEMO router | 1 | 2021-10-08 | ` | 2 | 4 | 2
| Ch 10 LAB: Set Up Mesh Wi-Fi Network | 2 | ` | 2021-09-22 | 3 | 6 | 3
#17 | Ch 11 reading | 2 | 2021-10-12 | ` | 4.75 | 8 | 3.25
| Ch 11 BTB: Security for Employees | 1 | ` | ` | 5.5 | 9 | 3.5
#18 | Ch 11 BTB: Passwords and Pass-phrases | 1 | 2021-10-18 | ` | 6.25 | 10 | 3.75
| Ch 11 BTB: Browser Security | 1 | ` | ` | 7 | 11 | 4
| Ch 12 reading | 1 | ` | ` | 7.75 | 12 | 4.25
#19 | Ch 12 LAB: Preventative Maintenance | 1 | 2021-10-20 | 2021-09-28 | 8.15 | 13 | 4.75
| Ch 12 BTB: Business Continuation and Disaster Recovery | 1 | ` | ` | 9 | 14 | 5
| Ch 13 reading | 1 | ` | ` | 9.75 | 15 | 5.25
#20 | Ch 13 BTB: Troubleshooting Scenario 1 | 1.5 | 2021-10-22 | ` | 11 | 16.5 | 5.5
| Ch 13 BTB: Troubleshooting Scenario 2 | 1.5 | ` | ` | 12.25 | 18 | 5.75
#21 | Review for Module 3 exam | 1 | 2021-10-26 | ` | 13 | 19 | 6
| M3 exam -- 46 questions in 1 hour (need 36.8 to pass) | 1 | ` | ` | 13.75 | 20 | 6.25
| review of results, signing off module | 1 | ` | ` | 14.5 | 21 | 6.5
|  | Module End Date | 2021-10-26 | 2021-09-28 | 38.75 | 63 | 24.25
Module 4: Database and Software Development |  | 18 hrs
#22 | Discussion about test prep, cert exam sign-up, ITPro.TV license | 0.25 | 2021-10-28 | 2021-09-28 | 0 | 0.25 | 0.25
| Fill out Certification Exam Sign Up sheet, show to instructor | 0.25 | ` | ` | 0 | 0.5 | 0.25
| Ch 14 sec 1: About Databases (videos) | 0.5 | ` | ` | 0.5 | 1 | 0.5
| Ch 14 sec 2: About RDBMS and SQL, Khan Academy tutorial | 2 | ` | ` | 1.5 | 3 | 1.5
#23 | Ch 14 SQL tutorial, Codecademy | 3 | 2021-11-02 | 2021-09-30 | 3.5 | 6 | 2.5
#24 | Ch 14 reading | 1 | 2021-11-04 | ` | 4 | 7 | 3
| Ch 14 Additional Reading, Ch 7 in second textbook | 1 | ` | ` | 4.75 | 8 | 3.25
| Ch 14 quiz | 0.5 | ` | ` | 5 | 8.5 | 3.5
| Ch 15 sec 1: Algorithms, Logic, Programming (videos) | 0.5 | ` | ` | 5 | 9 | 4
#25 | Ch 15 sec 2: Binary and Data (videos) | 0.5 | 2021-11-08 | 2021-10-04 | 5.25 | 9.5 | 4.25
| Ch 15 Binary Coding assignment | 0.5 | ` | ` | 5.75 | 10 | 4.5
| Ch 15 sec 3: Programming and SDLC (videos) | 0.5 | ` | ` | 5.75 | 10.5 | 4.75
| Ch 15 reading | 1 | ` | ` | 6.5 | 11.5 | 5
| Ch 15 Additional Reading, Ch 6 in second textbook | 0.5 | ` | ` | 6.75 | 12 | 5.25
#26 | Python tutorial | 3 | 2021-11-10 | ` | 9.25 | 15 | 5.75
#27 | Ch 15 quiz | 0.5 | 2021-11-12 | 2021-10-06 | 9.5 | 15.5 | 6
| Review for Module 4 exam | 1 | ` |  | 10 | 16.5 | 6.5
| M4 exam - 50 questions in 1 hr (need 40 to pass) | 1 | ` |  | 10.5 | 17.5 | 7
| review of results, signing off module | 0.5 | ` |  | 10.75 | 18 | 7.25
|  | Module End Date |  | 2021-10-26 | 49.5 | 81 | 31.5
Module 5: Study for Final Exam, Course Feedback and Final Exam |  | 9 hrs
#28 | Review for final exam | 3 | 2021-11-16 | 2021-10-26 | 1 | 3 | 2
#29 | Review for final exam | 3 | 2021-11-18 | ` | 2 | 6 | 4
#30 | Take CompTIA exam | 2 | 2021-11-22 | ` | 3.25 | 8 | 4.75
Return with results
| Complete course with activities in Canvas | 1 | 2021-11-29 | ` | 53.5 | 90 | 36.5